## 00 Overview
Smart Institute AI — Implementation Tracker
Source: Client Process Note (WTI Institution) + Smart Institution ERP & AI Functional Spec (Precious / approved by Heramb) ¦ MERN ¦ UI parity with Celeris ERP WTI (Dashboard / Masters / Transactions / Reports) | Arnav + Precious
Sheet | Scope | Item Count | Primary Owner
01 Architecture-Foundation | MERN scaffold, WTI-style ERP shell, merge-safe routing, shared UI kit, seeds, audit log | 20 | Arnav (scaffold) + shared routing contract
02 RBAC-Auth-Users | Roles, permissions, login, user management, permission-driven left nav (7 modules) | 15 | Arnav
03 Shared-Platform-Masters | Academic Year, Departments, Programs/Courses, Institution settings (foundation both consume) | 13 | Arnav owns models/APIs; Precious consumes
04 Admissions | Full admissions lifecycle: Masters + Transactions + Reports + AI OCR stub | 23 | Arnav
05 Students | Student lifecycle, hostel/transport, promotion, alumni | 14 | Arnav
06 Faculty | Faculty profiles, subject allocation, leave, performance | 16 | Precious
07 Academics | Curriculum, batches, timetable (AI-assist), attendance, internal assessments | 16 | Precious
08 LMS | Courses, content, assignments, quizzes, live class stub, progress | 11 | Precious
09 Exams | Scheduling, hall tickets, marks, results, transcripts, certificates | 12 | Precious
10 Fees | Fee structure, collection, receipts, scholarships, refunds, outstanding | 17 | Arnav
11 Dashboard-Reports | Institution dashboard + cross-module MIS; module reports owned with parent module | 10 | Split — see sheet
12 Phases-Acceptance | Phase 0–3 milestones, UI parity checklist vs erp.smart-aiapps.com/app/wti, UAT | 21 | Both
TOTAL TASKS | 188
MERGE-CONFLICT RULES (READ BEFORE CODING)
1. Arnav owns backend/routes/coreRoutes.js + frontend/src/routes/coreRoutes.jsx (Admissions, Students, Fees, Dashboard, Auth, Users, Shared Masters). Precious owns academicRoutes equivalents (Faculty, Academics, LMS, Exams). index only imports both aggregators.
2. Never edit the other dev's route aggregator; register new routes only in your own file (coreRoutes vs academicRoutes).
3. Arnav owns Layout.jsx, Sidebar.jsx, TopBar.jsx, theme tokens (Celeris/WTI look). Precious MUST NOT edit shell — add menu items via permission seeds + nav config keys only.
4. Shared components have a single owner (Notes column). Import — do not duplicate DataTable, PageHeader, MasterCardGrid, StatusBadge, etc.
5. Shared foundation masters (AcademicYear, Department, Program/Course) = Arnav. Precious consumes via API only — never edit those model files.
6. Student model + enrollment APIs = Arnav. Faculty/Academics/LMS/Exams read Student via API; do not fork Student schema.
7. Subject Master + Semester + Classroom + Batch = Precious (Academics). Admissions maps Program only; subject-level work stays with Precious.
8. Fee Structure / collection / receipt = Arnav. Admissions fee-payment confirmation calls Fees APIs owned by Arnav.
9. Phase 0 scaffold + shell + RBAC merged by Arnav before Precious starts feature branches.
10. Cross-module contracts (admission→student enrollment, fee.paid, exam.resultPublished, semester.promote) documented in docs/contracts.md — agree before coding.
11. UI parity: match Celeris ERP WTI patterns — left module nav, module tabs Dashboard¦Masters¦Transactions¦Reports, master card grid, blue banner module header. Reference: https://erp.smart-aiapps.com/app/wti/
12. Folder ownership: frontend/src/pages/admissions¦students¦fees¦dashboard + api/core/ = Arnav. pages/faculty¦academics¦lms¦exams + api/academic/ = Precious.

## 01 Architecture-Foundation
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
1. TECHNOLOGY STACK |  |  |  |  | Not Started
Stack | Monorepo | Project scaffold (backend/ + frontend/) | All | Root scripts; backend Node+Express .js; frontend React+Vite .jsx; .env.example for MONGO_URI, JWT_SECRET, PORT, CLIENT_URL. | Not Started | Arnav | Critical | Phase 0 | Precious clones after scaffold merged — do not scaffold in parallel.
Stack | Frontend | React 18 + Vite (frontend/) | Frontend | Responsive app; path aliases; ESLint. Mobile-friendly breakpoints for ERP tables. | Not Started | Arnav | Critical | Phase 0
Stack | Backend | Node.js + Express API (backend/) | Backend | REST folders: models/, routes/, controllers/, services/, middleware/, seeds/, utils/, config/. | Not Started | Arnav | Critical | Phase 0
Stack | Database | MongoDB + Mongoose connection | DB | config/db.js; GET /api/health. | Not Started | Arnav | Critical | Phase 0
Stack | Auth | JWT login + /api/auth/me | Backend | POST /api/auth/login; Bearer token; password_hash; /me returns user + permissions + institution context. | Not Started | Arnav | Critical | Phase 0
Stack | Charts | Recharts (or Chart.js) shared wrappers | Frontend | frontend/src/components/charts/ for dashboard + MIS reuse. | Not Started | Arnav | Medium | Phase 2 | Precious imports wrappers — does not rewrite chart kit.
Stack | Email | Email service stub (invoice/receipt later) | Backend | utils/mailer.js stub; env SMTP placeholders. Wired in Fees Phase 2 for Tax Invoice + Receipt auto-email (client process note). | Not Started | Arnav | High | Phase 2 | Aligns with client automated customer communication.
2. FOLDER STRUCTURE & MERGE-SAFE ROUTING |  |  |  |  | Not Started
Architecture | Route split | backend/routes/coreRoutes.js | Backend | Arnav mounts Admissions, Students, Fees, Dashboard, Auth, Users, Shared Masters here. | Not Started | Arnav | Critical | Phase 0 | Avoids both editing routes/index.js.
Architecture | Route split | backend/routes/academicRoutes.js | Backend | Precious mounts Faculty, Academics, LMS, Exams routes here. | Not Started | Precious | Critical | Phase 0
Architecture | Route split | frontend/src/routes/coreRoutes.jsx | Frontend | Lazy routes: auth, dashboard, admissions, students, fees, users, shared masters screens. | Not Started | Arnav | Critical | Phase 0
Architecture | Route split | frontend/src/routes/academicRoutes.jsx | Frontend | Lazy routes: faculty, academics, lms, exams. | Not Started | Precious | Critical | Phase 0
Architecture | App shell | WTI-style ERP Layout + Sidebar + TopBar | Frontend | Match Celeris WTI: collapsible left nav with 7 modules (Admissions, Students, Faculty, Academics, LMS, Exams, Fees); top context bar (workspace, search, FY, location); blue module banner. | Not Started | Arnav | Critical | Phase 0 | Precious does not edit Layout/Sidebar/TopBar.
Architecture | Module chrome | ModuleShell — Dashboard ¦ Masters ¦ Transactions ¦ Reports tabs | Frontend | Shared ModuleShell.jsx owned by Arnav; each module page composes it. Visual parity with /app/wti/masters card layout. | Not Started | Arnav | Critical | Phase 0 | Precious imports ModuleShell only.
Architecture | UI kit | Shared components: MasterCardGrid, DataTable, PageHeader, StatusBadge, FormDrawer | Frontend | frontend/src/components/ui/ — Celeris-like cards for Masters landing; tables for lists; consistent primary blue accents. | Not Started | Arnav | Critical | Phase 0 | Single owner; Precious imports.
Architecture | API client | api/client.js + api/core/ + api/academic/ | Frontend | Axios + auth interceptor; split API folders by owner (core = Arnav, academic = Precious). | Not Started | Arnav | High | Phase 0 | Precious creates only api/academic/* files.
Architecture | Institution context | models/Institution.js + FY/Location context | DB | Seed institution; financial year + location in TopBar (parity with ERP context bar). | Not Started | Arnav | High | Phase 0
Architecture | Error handling | Global error middleware + response envelope | Backend | { success, data, message } shape; 4xx/5xx handlers. | Not Started | Arnav | Medium | Phase 0
Architecture | Audit log | models/AuditLog.js + helper | Backend | Log admission approvals, fee overrides, result publish, permission changes, refunds. | Not Started | Arnav | High | Phase 0 | Precious calls writeAudit helper — does not edit model.
Architecture | Contracts doc | docs/contracts.md cross-module events | Docs | Document: admission.enrolled, fee.paid, result.published, student.promoted, student.alumni. | Not Started | Both | Critical | Phase 0 | Agree before feature coding.
Architecture | Seed runner | backend/seeds/index.js | Backend | Seed admin user, roles, permissions, institution, sample academic year. | Not Started | Arnav | Critical | Phase 0

## 02 RBAC-Auth-Users
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
STEP ZERO — ROLES & PERMISSIONS (BEFORE FEATURE MODULES) |  |  |  |  | Not Started
RBAC | DB | models/Role.js | DB | Seed roles: Super Admin, Institution Admin, Admission Officer, Faculty, Exam Controller, Accountant, Student (portal later). | Not Started | Arnav | Critical | Phase 0
RBAC | DB | models/Permission.js | DB | module + action (view¦create¦edit¦delete¦approve). Modules: admissions, students, faculty, academics, lms, exams, fees, dashboard, users, settings. | Not Started | Arnav | Critical | Phase 0
RBAC | DB | models/RolePermission.js | DB | M2M role↔permission; drives dynamic left nav. | Not Started | Arnav | Critical | Phase 0
RBAC | DB | models/UserMenuOverride.js | DB | Per-user grant/deny overrides. | Not Started | Arnav | High | Phase 0
RBAC | DB | models/User.js | DB | name, email, phone, password_hash, role_id, department_id?, is_active, linked_faculty_id?, linked_student_id?. | Not Started | Arnav | Critical | Phase 0
RBAC | Backend | middleware/requirePermission.js | Backend | requirePermission(module, action); resolves RolePermission + overrides. | Not Started | Arnav | Critical | Phase 0
RBAC | Backend | GET /api/auth/me permissions payload | Backend | Returns permission set for Sidebar + route guards. | Not Started | Arnav | Critical | Phase 0
RBAC | Frontend | PermissionContext + usePermission + ProtectedRoute | Frontend | No scattered role=== checks; menu built from permissions. | Not Started | Arnav | Critical | Phase 0
USER MANAGEMENT |  |  |  |  | Not Started
User Mgmt | Backend | CRUD /api/users | Backend | Create/edit/soft-deactivate; never hard-delete users with history. | Not Started | Arnav | Critical | Phase 0
User Mgmt | Backend | PUT /api/users/:id/permission-overrides | Backend | Admin toggles overrides. | Not Started | Arnav | High | Phase 1
User Mgmt | Frontend | pages/users/UserList.jsx + UserForm.jsx | Frontend | Admin-only user management screens inside shell. | Not Started | Arnav | High | Phase 1
User Mgmt | Frontend | pages/auth/Login.jsx | Frontend | Email + password; post-login redirect to Dashboard or first permitted module. | Not Started | Arnav | Critical | Phase 0 | UI clean/professional — match ERP login simplicity.
Nav | Seeds | Permission seeds for 7 left-nav modules | DB | Ensure Admissions, Students, Faculty, Academics, LMS, Exams, Fees appear when permitted. | Not Started | Arnav | Critical | Phase 0 | Precious requests new permission keys via seed PR owned by Arnav OR documents keys in contracts for Arnav to add.
Nav | Config | navConfig.js module metadata (icon, path, order) | Frontend | Single nav metadata file owned by Arnav; Precious only proposes new entries via PR note — Arnav merges nav keys. | Not Started | Arnav | Critical | Phase 0 | Prevents Sidebar edit conflicts.
Audit | Backend | Log permission & user changes | Backend | Write AuditLog on role/permission/user updates. | Not Started | Arnav | Medium | Phase 1

## 03 Shared-Platform-Masters
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
ARNAV — FOUNDATION MASTERS (PRECIOUS CONSUMES VIA API) |  |  |  |  | Not Started
Academic Year | DB | models/AcademicYear.js | DB | name, code, start_date, end_date, is_current, is_active. | Not Started | Arnav | Critical | Phase 1 | Maps to WTI Academic Year master + Admissions master list.
Academic Year | Backend | CRUD /api/academic-years | Backend | In coreRoutes; set-current endpoint. | Not Started | Arnav | Critical | Phase 1
Academic Year | Frontend | pages/settings/AcademicYearList/Form | Frontend | Masters-style list under Settings or Shared Masters; card entry from platform masters grid. | Not Started | Arnav | High | Phase 1
Department | DB | models/Department.js | DB | name, code, head_user_id?, is_active. | Not Started | Arnav | Critical | Phase 1 | WTI Department Master parity.
Department | Backend | CRUD /api/departments | Backend | coreRoutes. | Not Started | Arnav | Critical | Phase 1
Department | Frontend | pages/settings/DepartmentList/Form | Frontend | CRUD UI. | Not Started | Arnav | High | Phase 1
Program/Course | DB | models/Program.js (Course Master) | DB | name, code, department_id, duration, program_type (trade/diploma/degree), intake_default, is_active. Description field for WTI Course Master card. | Not Started | Arnav | Critical | Phase 1 | WTI Course Master; Precious links subjects later via program_id.
Program/Course | Backend | CRUD /api/programs | Backend | coreRoutes. | Not Started | Arnav | Critical | Phase 1
Program/Course | Frontend | pages/settings/ProgramList/Form | Frontend | Course master UI matching WTI card description: trade/diploma courses. | Not Started | Arnav | High | Phase 1
Institution Settings | DB/UI | Institution profile + FY display settings | All | Name, address, logo stub, default FY — TopBar context. | Not Started | Arnav | Medium | Phase 1
Shared Masters Hub | Frontend | pages/settings/SharedMastersHub.jsx | Frontend | Card grid (WTI Masters style) linking Academic Year, Department, Program — 11-module visual language. | Not Started | Arnav | High | Phase 1 | UI reference: /app/wti/masters.
API contracts | Docs | Document GET list shapes for Precious consumers | Docs | programs, departments, academic-years list DTOs in docs/contracts.md. | Not Started | Arnav | High | Phase 1 | Precious blocked until these APIs stable.
Seeds | DB | Seed sample AY, Depts, Programs | DB | Enough data for Faculty/Academics development. | Not Started | Arnav | High | Phase 1

## 04 Admissions
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
MODULE SHELL — ADMISSIONS |  |  |  |  | Not Started
Admissions | Frontend | Admissions module routes + ModuleShell tabs | Frontend | Dashboard ¦ Masters ¦ Transactions ¦ Reports under /admissions/* — same pattern as WTI. | Not Started | Arnav | Critical | Phase 1
Admissions | Frontend | Admissions Masters card grid | Frontend | Cards for: Academic Year (link), Admission Cycle, Programs, Departments (link), Intake, Categories, Eligibility, Document Checklist, Fee Mapping, Scholarship Rules, Statuses. | Not Started | Arnav | Critical | Phase 1 | Visual parity with WTI masters cards.
MASTERS |  |  |  |  | Not Started
Admission Cycle | DB | models/AdmissionCycle.js | DB | academic_year_id, name, start_date, end_date, status (draft¦open¦closed). | Not Started | Arnav | Critical | Phase 1
Intake Capacity | DB | models/IntakeCapacity.js | DB | cycle_id, program_id, category_id?, seats. | Not Started | Arnav | Critical | Phase 1
Admission Category | DB | models/AdmissionCategory.js | DB | name, code, quota_percent?, is_active. | Not Started | Arnav | Critical | Phase 1
Eligibility | DB | models/EligibilityCriteria.js | DB | program_id, min_qualification, min_marks, rules_json. | Not Started | Arnav | High | Phase 1
Document Checklist | DB | models/AdmissionDocumentType.js | DB | name, mandatory, applies_to_program_ids[]. | Not Started | Arnav | High | Phase 1
Fee Structure Mapping | DB | Admission↔FeeStructure link fields | DB | Map program + cycle to fee_structure_id (Fees module). | Not Started | Arnav | Critical | Phase 1 | Coordinates with Fees masters owned by Arnav.
Scholarship Rules | DB | models/ScholarshipRule.js (admission-facing) | DB | name, criteria_json, benefit_json; shared with Fees adjustments. | Not Started | Arnav | High | Phase 1
Admission Status | DB | Status enum/master | DB | Applied, Docs Pending, Eligible, Merit Listed, Allotted, Approved, Fee Pending, Enrolled, Rejected, Waitlisted. | Not Started | Arnav | Critical | Phase 1
Masters | Backend/UI | CRUD APIs + list/form pages for all admission masters | All | Each master: model, routes in coreRoutes, List+Form pages under pages/admissions/masters/. | Not Started | Arnav | Critical | Phase 1
TRANSACTIONS |  |  |  |  | Not Started
Application | DB | models/AdmissionApplication.js | DB | personal, academic, program_preferences[], category_id, cycle_id, status, merit_score?. | Not Started | Arnav | Critical | Phase 1
Application | Backend | POST/GET/PUT /api/admissions/applications | Backend | Register application; list/filter by cycle/status. | Not Started | Arnav | Critical | Phase 1
Documents | Backend | Document upload + verification endpoints | Backend | Upload files; verify/reject checklist items; AI OCR stub hook for authenticity/completeness. | Not Started | Arnav | High | Phase 1 | AI: OCR stub — flag Phase 2 for real OCR.
Eligibility | Backend | Eligibility validation service | Backend | Validate applicant vs program criteria; set Eligible/Ineligible. | Not Started | Arnav | Critical | Phase 1
Merit | Backend | Merit list generation | Backend | Rank by merit_score + category quotas; generate MeritList records. | Not Started | Arnav | Critical | Phase 1
Counseling | Backend | Seat allocation / counseling | Backend | Allot seats against IntakeCapacity; waitlist overflow. | Not Started | Arnav | Critical | Phase 1
Approval | Backend | Admission approval action | Backend | Committee approve/reject allotted seat; audit log. | Not Started | Arnav | Critical | Phase 1
Fee confirm | Backend | Fee payment confirmation → enrollment trigger | Backend | On fee.paid (Fees API), convert applicant → Student; generate roll_no + student_id. | Not Started | Arnav | Critical | Phase 1 | Contract: admission.enrolled.
Enrollment | Backend | Student enrollment service | Backend | Create Student from application; no re-entry of personal data. | Not Started | Arnav | Critical | Phase 1
Transactions UI | Frontend | Application list, detail, verify, allot, approve screens | Frontend | pages/admissions/transactions/* workflow screens. | Not Started | Arnav | Critical | Phase 1
REPORTS |  |  |  |  | Not Started
Reports | Backend/UI | Admission Summary, Application Status, Seat Availability, Pending, Merit List, Conversion | All | Filter by cycle/program; export CSV; charts where useful. | Not Started | Arnav | High | Phase 2 | Maps client: Student admission reports.
Dashboard | Frontend | Admissions mini-dashboard widgets | Frontend | Applications today, pending verify, seats left, conversion %. | Not Started | Arnav | Medium | Phase 2

## 05 Students
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
MODULE SHELL — STUDENTS |  |  |  |  | Not Started
Students | Frontend | Students ModuleShell + Masters card grid | Frontend | Masters cards: Categories, Status, Parent Relationship, Hostel Types, Transport Routes, Groups, Clubs. | Not Started | Arnav | Critical | Phase 1
MASTERS |  |  |  |  | Not Started
Student masters | DB | Category, Status, HostelType, TransportRoute, StudentGroup, Club models | DB | Config masters per functional spec. | Not Started | Arnav | Critical | Phase 1
Student masters | Backend/UI | CRUD APIs + pages for student masters | All | pages/students/masters/*. | Not Started | Arnav | High | Phase 1
CORE STUDENT |  |  |  |  | Not Started
Student | DB | models/Student.js | DB | student_id, roll_no, application_id?, personal, guardian[], program_id, academic_year_id, status, category_id, documents[]. | Not Started | Arnav | Critical | Phase 1 | Single owner — Precious reads via API only.
Student | Backend | CRUD /api/students + profile endpoints | Backend | Profile update, document management, search/directory. | Not Started | Arnav | Critical | Phase 1
Student | Frontend | StudentList, StudentProfile, DocumentManager | Frontend | Directory + profile tabs (personal, academic, guardian, docs). | Not Started | Arnav | Critical | Phase 1
TRANSACTIONS |  |  |  |  | Not Started
Hostel | DB/API/UI | Hostel allocation | All | Allocate hostel type/room; vacate; report. | Not Started | Arnav | Medium | Phase 2
Transport | DB/API/UI | Transport allocation | All | Assign route; report. | Not Started | Arnav | Medium | Phase 2
Medical | DB/API/UI | Medical records stub | All | Basic medical note records on student. | Not Started | Arnav | Low | Phase 3
Promotion | Backend/UI | Semester promotion | All | Promote based on Academics/Exams results signal; update semester standing. | Not Started | Arnav | Critical | Phase 2 | Consumes result.published / academics promotion contract from Precious.
Transfer | Backend/UI | Student transfer | All | Transfer program/campus fields; audit. | Not Started | Arnav | Medium | Phase 2
Alumni | Backend/UI | Alumni conversion | All | On graduation criteria → status Alumni; alumni directory. | Not Started | Arnav | High | Phase 2
Semester reg handoff | Backend | Expose enrolled students for Academics registration | Backend | GET students by program/semester for Precious Academics. | Not Started | Arnav | Critical | Phase 1
REPORTS |  |  |  |  | Not Started
Reports | All | Directory, Strength, Attendance Summary (read), Hostel, Transport, Alumni | All | Attendance summary may call Academics attendance API (Precious) read-only. | Not Started | Arnav | High | Phase 2 | Client: student records MIS.

## 06 Faculty
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
MODULE SHELL — FACULTY |  |  |  |  | Not Started
Faculty | Frontend | Faculty ModuleShell + Masters card grid | Frontend | Cards: Departments (read-only link), Designations, Faculty Types, Qualifications, Subject Masters, Workload Rules. Match WTI Faculty Master card tone. | Not Started | Precious | Critical | Phase 1 | Do not edit Department model — consume Arnav API.
MASTERS |  |  |  |  | Not Started
Designation | DB | models/Designation.js | DB | name, code, is_active. | Not Started | Precious | Critical | Phase 1
Faculty Type | DB | models/FacultyType.js | DB | Permanent/Visiting/Trainer etc. | Not Started | Precious | High | Phase 1
Qualification | DB | models/QualificationMaster.js | DB | degree/cert list for faculty profiles. | Not Started | Precious | Medium | Phase 1
Subject Master | DB | models/Subject.js | DB | name, code, program_id, theory/practical flag, credits — WTI Subject Master. | Not Started | Precious | Critical | Phase 1 | Arnav Admissions does not own subjects.
Workload Rules | DB | models/WorkloadRule.js | DB | max_hours_per_week, designation_id?, rules_json. | Not Started | Precious | High | Phase 1
Masters | Backend/UI | CRUD for faculty masters + Subject | All | academicRoutes; pages/faculty/masters/*. | Not Started | Precious | Critical | Phase 1
TRANSACTIONS |  |  |  |  | Not Started
Faculty | DB | models/Faculty.js | DB | employee_code, personal, department_id, designation_id, type_id, qualifications[], subjects[], user_id?, is_active. | Not Started | Precious | Critical | Phase 1 | WTI Faculty Master profiles.
Faculty | Backend/UI | Faculty registration CRUD + directory | All | Register, map department/designation, link optional User. | Not Started | Precious | Critical | Phase 1
Subject allocation | Backend/UI | Assign subjects to faculty | All | Respect workload rules + specialization. | Not Started | Precious | Critical | Phase 1
Timetable assign | Backend | API for Academics to attach faculty to slots | Backend | Expose faculty availability helpers used by Academics timetable. | Not Started | Precious | Critical | Phase 1 | Same owner as Academics — ok to share services.
Attendance | Backend/UI | Faculty attendance / punch or mark | All | Daily faculty attendance records. | Not Started | Precious | High | Phase 2 | Client: Faculty and attendance reports.
Leave | Backend/UI | Leave management | All | Apply/approve leave; block timetable conflicts later. | Not Started | Precious | High | Phase 2
Performance | Backend/UI | Performance evaluation stub | All | Periodic rating records + dashboard widgets. | Not Started | Precious | Medium | Phase 3
Research/Training | Backend/UI | Research & training records | All | Publications + training log on faculty profile. | Not Started | Precious | Low | Phase 3
REPORTS |  |  |  |  | Not Started
Reports | All | Faculty Directory, Workload, Attendance, Leave, Performance Dashboard | All | pages/faculty/reports/*. | Not Started | Precious | High | Phase 2

## 07 Academics
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
MODULE SHELL — ACADEMICS |  |  |  |  | Not Started
Academics | Frontend | Academics ModuleShell + Masters cards | Frontend | Programs (read), Semesters, Subjects (link), Curriculum, Credits, Academic Calendar, Classrooms, TimeSlots, Batches — WTI Batch/Classroom/Semester parity. | Not Started | Precious | Critical | Phase 1
MASTERS |  |  |  |  | Not Started
Semester | DB | models/Semester.js | DB | name, number, academic_year_id, start/end, is_active — WTI Semester master. | Not Started | Precious | Critical | Phase 1
Batch | DB | models/Batch.js | DB | name, program_id, academic_year_id, semester_id?, capacity — WTI Batch Master. | Not Started | Precious | Critical | Phase 1
Classroom | DB | models/Classroom.js | DB | name, type (classroom¦lab¦workshop), capacity — WTI Classroom master. | Not Started | Precious | Critical | Phase 1
Time Slot | DB | models/TimeSlot.js | DB | label, start_time, end_time, day_optional. | Not Started | Precious | Critical | Phase 1
Curriculum | DB | models/Curriculum.js + CurriculumSubject | DB | program_id, semester_id, subject_id, credits, is_elective. | Not Started | Precious | Critical | Phase 1
Academic Calendar | DB | models/AcademicCalendarEvent.js | DB | events: term start/end, holidays, exam windows. | Not Started | Precious | High | Phase 1
Masters | Backend/UI | CRUD APIs + pages for academics masters | All | academicRoutes; pages/academics/masters/*. | Not Started | Precious | Critical | Phase 1
TRANSACTIONS |  |  |  |  | Not Started
Registration | Backend/UI | Semester + subject registration | All | Register student (from Arnav Students API) into semester subjects. | Not Started | Precious | Critical | Phase 1 | Consume Students API — no Student model edits.
Batch allocation | Backend/UI | Allocate students to batches | All | Batch membership records. | Not Started | Precious | Critical | Phase 1
Timetable | DB | models/TimetableSlot.js | DB | batch_id, subject_id, faculty_id, classroom_id, day, time_slot_id. | Not Started | Precious | Critical | Phase 1
Timetable | Backend | AI-assisted conflict-free timetable generator | Backend | Detect faculty/classroom/batch conflicts; generate draft; publish. | Not Started | Precious | Critical | Phase 2 | AI capability per functional spec.
Timetable | Frontend | Timetable grid UI + publish | Frontend | Weekly grid; conflict highlights. | Not Started | Precious | Critical | Phase 2
Attendance | DB/API/UI | Student class attendance | All | Mark per timetable slot; store attendance records. | Not Started | Precious | Critical | Phase 1 | Client faculty/attendance reports feed.
Assignments/IA | Backend/UI | Assignment creation + internal assessments | All | Internal marks components before Exams module finals. | Not Started | Precious | High | Phase 2
REPORTS |  |  |  |  | Not Started
Reports | All | Timetable, Attendance, Academic Progress, Course Completion, Class Utilization | All | pages/academics/reports/*. | Not Started | Precious | High | Phase 2 | Client: scheduling + institutional MIS pieces.

## 08 LMS
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
MODULE SHELL — LMS |  |  |  |  | Not Started
LMS | Frontend | LMS ModuleShell + Masters cards | Frontend | Course Categories, Learning Paths, Assignment Templates, Quiz Templates, Assessment Types. | Not Started | Precious | Critical | Phase 2
MASTERS |  |  |  |  | Not Started
LMS masters | DB | Category, LearningPath, AssignmentTemplate, QuizTemplate, AssessmentType | DB | Config masters per spec. | Not Started | Precious | High | Phase 2
LMS masters | Backend/UI | CRUD + master pages | All | pages/lms/masters/*. | Not Started | Precious | High | Phase 2
TRANSACTIONS |  |  |  |  | Not Started
Course | DB | models/LmsCourse.js | DB | title, subject_id?, faculty_id, modules/topics, objectives, published. | Not Started | Precious | Critical | Phase 2
Content | Backend/UI | Content upload + publish | All | Files/links/videos metadata; publish to enrolled students. | Not Started | Precious | Critical | Phase 2
Enrollment sync | Backend | Enroll students from Academics batch/subject | Backend | Pull registered students via Academics/Students APIs. | Not Started | Precious | Critical | Phase 2
Assignment/Quiz | Backend/UI | Create assignments & quizzes; student submission | All | Submission records; due dates. | Not Started | Precious | Critical | Phase 2
Forums/Live | Backend/UI | Discussion forums + live class stub | All | Forum threads; live class link stub (Zoom/Meet URL). | Not Started | Precious | Medium | Phase 3
Evaluation | Backend/UI | Evaluate submissions + AI-assist stub | All | Scores + feedback; AI grading assist stub. | Not Started | Precious | High | Phase 2
Progress | Backend | Learning progress + course completion | Backend | Realtime progress %; completion status. | Not Started | Precious | Critical | Phase 2
REPORTS |  |  |  |  | Not Started
Reports | All | Learning Progress, Course Completion, Assignment Status, Quiz Analytics, Engagement | All | pages/lms/reports/*. | Not Started | Precious | High | Phase 2

## 09 Exams
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
MODULE SHELL — EXAMS |  |  |  |  | Not Started
Exams | Frontend | Exams ModuleShell + Masters cards | Frontend | Exam Types, Grading Scheme, Passing Rules, Evaluation Rules, Result Templates. | Not Started | Precious | Critical | Phase 2
MASTERS |  |  |  |  | Not Started
Exam masters | DB | ExamType, GradingScheme, PassingRule, EvaluationRule, ResultTemplate | DB | Config per functional spec. | Not Started | Precious | Critical | Phase 2
Exam masters | Backend/UI | CRUD + pages | All | pages/exams/masters/*. | Not Started | Precious | Critical | Phase 2
TRANSACTIONS |  |  |  |  | Not Started
Schedule | DB/API/UI | Exam scheduling | All | Dates, subjects, rules; publish to students. | Not Started | Precious | Critical | Phase 2
Hall ticket | Backend/UI | Hall ticket generation | All | Eligible students; PDF/print stub; center/seating info. | Not Started | Precious | Critical | Phase 2
Seating | Backend/UI | Seating arrangement | All | Allocate seats/rooms for exam sessions. | Not Started | Precious | High | Phase 2
Marks | Backend/UI | Theory + practical mark entry | All | Faculty/evaluator entry; lock after submit. | Not Started | Precious | Critical | Phase 2
Results | Backend | Result processing vs grading/passing rules | Backend | Compute grades; backlog flags. | Not Started | Precious | Critical | Phase 2
Publish | Backend/UI | Publish results + notify student record | All | Emit result.published for Students/Academics promotion consumers. | Not Started | Precious | Critical | Phase 2 | Contract for Arnav promotion.
Revaluation | Backend/UI | Revaluation workflow | All | Request → re-enter marks → revise result. | Not Started | Precious | Medium | Phase 3
Transcript/Certificate | Backend/UI | Transcript + certificate generation | All | PDF stubs; store documents on student via API or local exam docs table referencing student_id. | Not Started | Precious | High | Phase 2 | Client: certification and examination management.
REPORTS |  |  |  |  | Not Started
Reports | All | Result Analysis, Grade Distribution, Pass %, Subject Analysis, Topper, Backlog | All | pages/exams/reports/*. | Not Started | Precious | High | Phase 2

## 10 Fees
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
MODULE SHELL — FEES |  |  |  |  | Not Started
Fees | Frontend | Fees ModuleShell + Masters cards | Frontend | Fee Structure, Fee Heads, Payment Modes, Installments, Scholarships, Fine/Penalty, Tax, Refund Policies. | Not Started | Arnav | Critical | Phase 1 | Client billing→receipt + auto email.
MASTERS |  |  |  |  | Not Started
Fee Head | DB | models/FeeHead.js | DB | name, code, tax_applicable, is_active. | Not Started | Arnav | Critical | Phase 1
Fee Structure | DB | models/FeeStructure.js | DB | program_id, academic_year_id, heads[], installment_plan_id?, total. | Not Started | Arnav | Critical | Phase 1
Payment Mode | DB | models/PaymentMode.js | DB | cash, UPI, card, bank, online gateway stub. | Not Started | Arnav | High | Phase 1
Installment Plan | DB | models/InstallmentPlan.js | DB | schedule JSON: due dates / percentages. | Not Started | Arnav | High | Phase 1
Fine/Tax/Refund | DB | FineRule, TaxConfig, RefundPolicy models | DB | Per functional spec masters. | Not Started | Arnav | High | Phase 1
Masters | Backend/UI | CRUD + fee master pages | All | pages/fees/masters/*. | Not Started | Arnav | Critical | Phase 1
TRANSACTIONS |  |  |  |  | Not Started
Assignment | Backend/UI | Generate + assign fees to students | All | Map structure to enrolled students; admission fee assignment. | Not Started | Arnav | Critical | Phase 1
Collection | DB | models/FeePayment.js + StudentFeeLedger | DB | Payments online/offline; installment tracking; outstanding. | Not Started | Arnav | Critical | Phase 1
Collection | Backend/UI | Collect payment screens + APIs | All | Record payment; update ledger. | Not Started | Arnav | Critical | Phase 1
Receipt | Backend | Auto receipt generation on successful payment | Backend | Digital receipt number; PDF stub; store electronic record. | Not Started | Arnav | Critical | Phase 1 | Client process note requirement.
Tax Invoice | Backend | Tax Invoice generation on payment confirmation | Backend | Generate tax invoice; email invoice + receipt to registered email (mailer). | Not Started | Arnav | Critical | Phase 2 | Client automated communication.
Scholarship/Fine | Backend/UI | Scholarship adjustment + fine calculation | All | Adjust dues; apply fines per rules. | Not Started | Arnav | High | Phase 2
Refund | Backend/UI | Refund processing | All | Refund workflow + policy checks; audit. | Not Started | Arnav | High | Phase 2
Outstanding | Backend/UI | Outstanding fee management | All | Lists, reminders stub, block hall ticket flag API for Exams consumer. | Not Started | Arnav | High | Phase 2 | Precious Exams reads dues flag via API.
Admission bridge | Backend | Admission fee payment confirmation API | Backend | Endpoint/event used by Admissions enrollment step. | Not Started | Arnav | Critical | Phase 1 | Same owner — internal contract.
REPORTS |  |  |  |  | Not Started
Reports | All | Collection, Outstanding, Daily Collection, Student Ledger, Scholarship, Refund, Revenue Dashboard | All | Also Invoice Status, Receipt Generation, Ageing-style outstanding (client finance-lite). | Not Started | Arnav | High | Phase 2 | Client: Fee collection reports + course-wise profitability later.

## 11 Dashboard-Reports
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
INSTITUTION DASHBOARD |  |  |  |  | Not Started
Dashboard | Frontend | pages/dashboard/InstitutionDashboard.jsx | Frontend | WTI-style dashboard home: admissions funnel, student strength, fee collection MTD, upcoming exams, attendance snapshot, pending approvals. | Not Started | Arnav | Critical | Phase 2 | Shell/layout already Arnav; widgets call module APIs.
Dashboard | Backend | GET /api/dashboard/summary | Backend | Aggregates counts Arnav owns (admissions, students, fees); embeds optional precious metrics via HTTP internal calls or shared read models. | Not Started | Arnav | Critical | Phase 2 | Agree metric contracts with Precious.
Dashboard | Frontend | Pending tasks / approvals widget | Frontend | Pending admission approvals, pending fee follow-ups — process visibility per client note. | Not Started | Arnav | High | Phase 2
PRECIOUS — MODULE DASHBOARD WIDGETS |  |  |  |  | Not Started
Dashboard APIs | Backend | GET /api/dashboard/faculty-academics-summary | Backend | Faculty count, today's classes, attendance %, open exams — academicRoutes. | Not Started | Precious | High | Phase 2 | Arnav dashboard consumes this read API only.
Dashboard APIs | Backend | GET /api/dashboard/lms-exams-summary | Backend | LMS engagement + exam schedule/result publish stats. | Not Started | Precious | Medium | Phase 2
CROSS-MODULE MIS |  |  |  |  | Not Started
MIS | Reports | Institutional MIS report page (admin) | Frontend | Combined MIS: admissions conversion, fee collection, attendance, pass % — tabs; Arnav page composing APIs. | Not Started | Arnav | High | Phase 3 | Client: Institutional MIS reports.
MIS | Reports | Course-wise profitability (fees vs cost stub) | All | Revenue by program from Fees; cost stub fields — Phase 3. | Not Started | Arnav | Medium | Phase 3 | Client: Course-wise profitability reports.
Compliance | Reports | Compliance & audit report stub | All | Export audit log filters; compliance checklist stub. | Not Started | Arnav | Medium | Phase 3 | Client: Compliance and audit reports.
UI parity | Frontend | Dashboard visual match to WTI Dashboard | Frontend | Spacing, cards, banner, KPI tiles consistent with reference ERP. | Not Started | Arnav | High | Phase 2 | Reference /app/wti/dashboard.
Module reports registry | Docs | List each module report owner + path | Docs | Ensure every report in functional spec is tracked Done in module sheets. | Not Started | Both | Medium | Phase 2

## 12 Phases-Acceptance
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
PHASE MILESTONES |  |  |  |  | Not Started
Phase 0 | Milestone | Scaffold + merge-safe routing + ERP shell + RBAC + login merged | All | Precious can branch; nav shows 7 modules (empty shells ok). | Not Started | Both | Critical | Phase 0 | Arnav merges first.
Phase 0 | UI | Left nav labels exactly: Admissions, Students, Faculty, Academics, LMS, Exams, Fees | Frontend | Order and naming locked. | Not Started | Arnav | Critical | Phase 0
Phase 0 | UI | ModuleShell tabs Dashboard ¦ Masters ¦ Transactions ¦ Reports on each module stub | Frontend | Empty states with WTI-like banner. | Not Started | Arnav | Critical | Phase 0 | Precious uses same shell for owned modules.
Phase 1 | Milestone | Shared masters + Admissions + Students + Fees core + Faculty masters/profiles + Academics masters/registration/attendance | All | End-to-end: apply → pay → enroll → appear in academics registration. | Not Started | Both | Critical | Phase 1
Phase 1 | Contract test | admission.enrolled creates Student readable by Precious | All | Integration smoke test documented. | Not Started | Both | Critical | Phase 1
Phase 2 | Milestone | Timetable AI, LMS core, Exams core, Fee tax invoice email, Dashboards, major reports | All | Teaching/learning/exam/fee loop working. | Not Started | Both | Critical | Phase 2
Phase 2 | Contract test | result.published usable for promotion; dues flag blocks hall ticket | All | Cross-module smoke tests. | Not Started | Both | Critical | Phase 2
Phase 3 | Milestone | Alumni, revaluation, forums/live polish, performance, profitability/compliance MIS, AI OCR real integration optional | All | Polish + advanced items. | Not Started | Both | High | Phase 3
UI PARITY CHECKLIST (vs Celeris WTI) |  |  |  |  | Not Started
UI | Parity | Left sidebar module list styling | Frontend | Active state, icons, collapsible behavior similar to reference. | Not Started | Arnav | High | Phase 0 | https://erp.smart-aiapps.com/app/wti/dashboard
UI | Parity | Top context bar (workspace, search, FY, location) | Frontend | Present on all pages. | Not Started | Arnav | High | Phase 0
UI | Parity | Blue module banner title + subtitle + badge count on Masters | Frontend | Masters landing shows module count badge like '11 MODULES'. | Not Started | Arnav | High | Phase 1
UI | Parity | Masters card grid: icon, title, description, Open module link | Frontend | Same interaction pattern as WTI Masters. | Not Started | Arnav | Critical | Phase 1 | Precious follows same card component.
UI | Parity | List/table pages consistent density and primary actions | Frontend | Shared DataTable. | Not Started | Both | High | Phase 1
UAT / ACCEPTANCE |  |  |  |  | Not Started
UAT | Admissions | Full workflow application→enrollment with fee payment | All | Demo script pass. | Not Started | Arnav | Critical | Phase 1
UAT | Students | Profile, hostel/transport, promotion, alumni path | All | Demo script pass. | Not Started | Arnav | High | Phase 2
UAT | Faculty/Academics | Faculty assign → timetable → attendance | All | Demo script pass. | Not Started | Precious | Critical | Phase 2
UAT | LMS/Exams | Course content → submission → exam → result publish | All | Demo script pass. | Not Started | Precious | Critical | Phase 2
UAT | Fees | Assign, collect, receipt, email invoice/receipt, outstanding | All | Demo script pass per client process note. | Not Started | Arnav | Critical | Phase 2
UAT | E2E | Single student journey application to alumni (happy path) | All | No duplicate data entry across modules. | Not Started | Both | Critical | Phase 3
UAT | RBAC | Each role sees only permitted nav modules/actions | All | Permission matrix verified. | Not Started | Arnav | Critical | Phase 1
Docs | Handoff | README + seed credentials + tracker status updated | Docs | Keep this tracker Status column current as work proceeds. | Not Started | Both | High | Phase 0